## Data (2) (hidden)
Defect Report |  |  |  | Date: | 2012-04-19
Claimed Fixed: |  |  | 21
| BURN DOWN | [11 empty] | DETAILED HISTORY
| Day / Date |  | PLANNED |  | ACTUAL | [5 empty] | ACTUAL VS PLANNED
|  |  | Planned Fix Rate | Planned Total Remaining | Created | Closed Fixed | Resolved Pool | Fix Rate | Total Resolved and Open defects | Total Open | Delta Fix Rate | Delta Backlog | Blocker 1 | Blocker 2 | Blockers | Critical 3 | Critical 4 | Critical 5 | Criticals | Major 6 | Major 7 | Major 8 | Majors | BCM Count
| Thursday | 2012-01-19 | 9 | 300 | 48 | 101 | 101 | 53 | 398 | 297 | 44 | -3 | 4 | 41 | 45 | 29 | 0 | 57 | 86 | 14 | 0 | 154 | 168 | 299
| Friday | 2012-01-20 | 9 | 290 | 34 | 4 | 4 | -30 | 331 | 327 | -39 | 37 | 2 | 46 | 48 | 30 | 0 | 58 | 88 | 18 | 0 | 173 | 191 | 327
| Monday | 2012-01-23 | 9 | 280 | 16 | 20 | 20 | 4 | 343 | 323 | -5 | 43 | 2 | 47 | 49 | 30 | 0 | 59 | 89 | 17 | 0 | 168 | 185 | 323
| Tuesday | 2012-01-24 | 9 | 270 | 18 | 26 | 26 | 8 | 341 | 315 | -1 | 45 | 3 | 40 | 43 | 32 | 0 | 58 | 90 | 15 | 0 | 167 | 182 | 315
| Wednesday | 2012-01-25 | 9 | 260 | 14 | 3 | 3 | -11 | 329 | 326 | -20 | 66 | 3 | 40 | 43 | 32 | 0 | 62 | 94 | 15 | 0 | 174 | 189 | 326
| Thursday | 2012-01-26 | 9 | 250 | 4 | 3 | 3 | -1 | 330 | 327 | -10 | 77 | 3 | 37 | 40 | 32 | 0 | 63 | 95 | 15 | 0 | 177 | 192 | 327
| Friday | 2012-01-27 | 9 | 240 | 3 | 7 | 7 | 4 | 330 | 323 | -5 | 83 | 3 | 36 | 39 | 32 | 0 | 62 | 94 | 15 | 0 | 175 | 190 | 323
| Monday | 2012-01-30 | 9 | 230 | 2 | 11 | 11 | 9 | 325 | 314 | 0 | 84 | 3 | 28 | 31 | 32 | 0 | 63 | 95 | 15 | 0 | 173 | 188 | 314
| Tuesday | 2012-01-31 | 9 | 220 | 3 | 5 | 5 | 2 | 317 | 312 | -7 | 92 | 2 | 28 | 30 | 31 | 0 | 64 | 95 | 15 | 0 | 172 | 187 | 312
| Wednesday | 2012-02-01 | 9 | 210 | 8 | 4 | 4 | -4 | 319 | 315 | -13 | 105 | 2 | 26 | 28 | 31 | 0 | 63 | 94 | 15 | 0 | 178 | 193 | 315
| Thursday | 2012-02-02 | 9 | 200 | 7 | 52 | 52 | 45 | 322 | 270 | 36 | 70 | 2 | 20 | 22 | 23 | 0 | 53 | 76 | 12 | 0 | 160 | 172 | 270
| Friday | 2012-02-03 | 9 | 190 | 3 | 24 | 24 | 21 | 273 | 249 | 12 | 59 | 2 | 17 | 19 | 21 | 0 | 49 | 70 | 11 | 0 | 149 | 160 | 249
| Monday | 2012-02-06 | 9 | 180 | 15 | 26 | 26 | 11 | 264 | 238 | 2 | 58 | 2 | 12 | 14 | 22 | 0 | 46 | 68 | 11 | 0 | 145 | 156 | 238
| Tuesday | 2012-02-07 | 9 | 170 | 12 | 12 | 12 | 0 | 250 | 238 | -9 | 68 | 2 | 10 | 12 | 19 | 0 | 47 | 66 | 7 | 0 | 153 | 160 | 238
| Wednesday | 2012-02-08 | 9 | 160 | 9 | 7 | 7 | -2 | 247 | 240 | -11 | 80 | 2 | 11 | 13 | 16 | 0 | 52 | 68 | 7 | 0 | 152 | 159 | 240
| Thursday | 2012-02-09 | 9 | 150 | 8 | 26 | 26 | 18 | 248 | 222 | 9 | 72 | 2 | 9 | 11 | 16 | 0 | 46 | 62 | 5 | 0 | 144 | 149 | 222
| Friday | 2012-02-10 | 9 | 140 | 8 | 0 | 0 | -8 | 229 | 229 | -17 | 89 | 2 | 11 | 13 | 16 | 0 | 47 | 63 | 5 | 0 | 148 | 153 | 229
| Monday | 2012-02-13 | 9 | 130 | 23 | 0 | 0 | -23 | 251 | 251 | -32 | 121 | 2 | 12 | 14 | 16 | 0 | 48 | 64 | 5 | 0 | 168 | 173 | 251
| Tuesday | 2012-02-14 | 9 | 120 | 1 | 0 | 0 | -1 | 252 | 252 | -10 | 132 | 2 | 12 | 14 | 16 | 0 | 49 | 65 | 5 | 0 | 168 | 173 | 252
| Wednesday | 2012-02-15 | 9 | 110 | 7 | 0 | 0 | -7 | 255 | 255 | -16 | 145 | 2 | 13 | 15 | 17 | 0 | 50 | 67 | 5 | 0 | 168 | 173 | 255
| Thursday | 2012-02-16 | 9 | 100 | 5 | 45 | 45 | 40 | 260 | 215 | 31 | 115 | 2 | 9 | 11 | 16 | 0 | 35 | 51 | 3 | 0 | 150 | 153 | 215
| Friday | 2012-02-17 | 9 | 90 | 4 | 54 | 54 | 50 | 219 | 165 | 41 | 75 | 1 | 5 | 6 | 12 | 0 | 28 | 40 | 4 | 0 | 115 | 119 | 165
| Monday | 2012-02-20 | 9 | 164 | 10 | 7 | 7 | -3 | 175 | 168 | -12 | 4 | 1 | 4 | 5 | 11 | 0 | 28 | 39 | 3 | 0 | 121 | 124 | 168
| Tuesday | 2012-02-21 | 9 | 155 | 3 | 13 | 13 | 10 | 171 | 158 | 1 | 3 | 1 | 4 | 5 | 9 | 0 | 25 | 34 | 3 | 0 | 116 | 119 | 158
| Wednesday | 2012-02-22 | 9 | 146 | 1 | 15 | 15 | 14 | 159 | 144 | 5 | -2 | 1 | 4 | 5 | 7 | 0 | 24 | 31 | 3 | 0 | 105 | 108 | 144
| Thursday | 2012-02-23 | 9 | 137 | 9 | 10 | 10 | 1 | 153 | 143 | -8 | 6 | 1 | 4 | 5 | 6 | 0 | 23 | 29 | 2 | 0 | 107 | 109 | 143
| Friday | 2012-02-24 | 9 | 128 | 5 | 9 | 9 | 4 | 147 | 138 | -5 | 10 | 1 | 5 | 6 | 6 | 0 | 24 | 30 | 1 | 0 | 101 | 102 | 138
| Monday | 2012-02-27 | 9 | 119 | 17 | 9 | 9 | -8 | 155 | 146 | -17 | 27 | 2 | 5 | 7 | 6 | 0 | 26 | 32 | 1 | 0 | 106 | 107 | 146
| Tuesday | 2012-02-28 | 9 | 110 | 20 | 12 | 12 | -8 | 166 | 154 | -17 | 44 | 1 | 5 | 6 | 6 | 0 | 24 | 30 | 1 | 0 | 117 | 118 | 154
| Wednesday | 2012-02-29 | 9 | 101 | 8 | 29 | 29 | 21 | 162 | 133 | 12 | 32 | 1 | 4 | 5 | 6 | 0 | 26 | 32 | 1 | 0 | 95 | 96 | 133
| Thursday | 2012-03-01 | 9 | 92 | 6 | 9 | 9 | 3 | 139 | 130 | -6 | 38 | 1 | 4 | 5 | 7 | 0 | 23 | 30 | 1 | 0 | 94 | 95 | 130
| Friday | 2012-03-02 | 9 | 83 | 6 | 4 | 4 | -2 | 136 | 132 | -11 | 49 | 1 | 4 | 5 | 7 | 0 | 24 | 31 | 1 | 0 | 95 | 96 | 132
| Monday | 2012-03-05 | 7 | 76 | 5 | 13 | 13 | 8 | 136 | 123 | 1 | 47 | 1 | 4 | 5 | 6 | 0 | 25 | 31 | 0 | 0 | 87 | 87 | 123
| Tuesday | 2012-03-06 | 7 | 69 | 4 | 33 | 33 | 29 | 126 | 93 | 22 | 24 | 0 | 2 | 2 | 6 | 0 | 18 | 24 | 0 | 0 | 67 | 67 | 93
| Wednesday | 2012-03-07 | 7 | 62 | 5 | 10 | 10 | 5 | 98 | 88 | -2 | 26 | 0 | 2 | 2 | 7 | 0 | 15 | 22 | 0 | 0 | 64 | 64 | 88
| Thursday | 2012-03-08 | 7 | 55 | 6 | 8 | 8 | 2 | 92 | 84 | -5 | 29 | 0 | 1 | 1 | 8 | 0 | 12 | 20 | 0 | 0 | 63 | 63 | 84
| Friday | 2012-03-09 | 7 | 50 | 10 | 2 | 13 | -8 | 97 | 84 | -15 | 34 | 0 | 1 | 1 | 8 | 0 | 11 | 19 | 0 | 0 | 64 | 64 | 84
| Monday | 2012-03-12 | 0 | 50 | 2 | 0 | 13 | -2 | 97 | 84 | -2 | 34 | 0 | 1 | 1 | 8 | 0 | 11 | 19 | 0 | 0 | 64 | 64 | 84
| Tuesday | 2012-03-13 | 0 | 50 | 3 | 1 | 25 | -2 | 95 | 70 | -2 | 20 | 0 | 2 | 2 | 5 | 0 | 7 | 12 | 0 | 0 | 56 | 56 | 70
| Wednesday | 2012-03-14 | 0 | 50 | 0 | 2 | 30 | 2 | 92 | 62 | 2 | 12 | 0 | 1 | 1 | 6 | 0 | 6 | 12 | 0 | 0 | 49 | 49 | 62
| Thursday | 2012-03-15 | 0 | 50 | 3 | 6 | 12 | 3 | 78 | 66 | 3 | 16 | 0 | 1 | 1 | 4 | 0 | 6 | 10 | 1 | 0 | 54 | 55 | 66
| Friday | 2012-03-16 | 0 | 50 | 8 | 1 | 21 | -7 | 78 | 57 | -7 | 7 | 0 | 1 | 1 | 3 | 0 | 3 | 6 | 1 | 0 | 49 | 50 | 57
| Monday | 2012-03-19 | 0 | 50 | 7 | 21 | 20 | 14 | 77 | 57 | 14 | 7 | 0 | 3 | 3 | 3 | 0 | 5 | 8 | 0 | 0 | 46 | 46 | 57
| Tuesday | 2012-03-20 | 0 | 50 | 6 | 1 | 21 | -5 | 84 | 63 | -5 | 13 | 0 | 2 | 2 | 3 | 0 | 6 | 9 | 1 | 0 | 51 | 52 | 63
| Wednesday | 2012-03-21 | 0 | 50 | 1 | 0 | 17 | -1 | 73 | 56 | -1 | 6 | 0 | 1 | 1 | 2 | 0 | 5 | 7 | 1 | 0 | 47 | 48 | 56
| Thursday | 2012-03-22 | 0 | 50 | 4 | 13 | 14 | 9 | 70 | 56 | 9 | 6 | 0 | 2 | 2 | 2 | 0 | 8 | 10 | 1 | 0 | 43 | 44 | 56
| Friday | 2012-03-23 | 0 | 50 | 4 | 20 | 18 | 16 | 73 | 55 | 16 | 5 | 0 | 3 | 3 | 2 | 0 | 9 | 11 | 1 | 0 | 40 | 41 | 55
| Monday | 2012-03-26 | 0 | 50 | 0 | 1 | 9 | 1 | 58 | 49 | 1 | -1 | 0 | 3 | 3 | 2 | 0 | 5 | 7 | 2 | 0 | 37 | 39 | 49
| Tuesday | 2012-03-27 | 0 | 50 | 3 | 4 | 13 | 1 | 55 | 42 | 1 | -8 | 0 | 2 | 2 | 2 | 0 | 4 | 6 | 2 | 0 | 32 | 34 | 42
| Wednesday | 2012-03-28 | 0 | 50 | 0 | 8 | 15 | 8 | 50 | 35 | 8 | -15 | 0 | 1 | 1 | 2 | 0 | 2 | 4 | 2 | 0 | 28 | 30 | 35
| Thursday | 2012-03-29 | 0 | 50 | 5 | 4 | 20 | -1 | 50 | 30 | -1 | -20 | 0 | 0 | 0 | 1 | 0 | 2 | 3 | 2 | 0 | 25 | 27 | 30
| Friday | 2012-03-30 | 0 | 50 | 4 | 7 | 21 | 3 | 49 | 28 | 3 | -22 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 25 | 27 | 28
| Monday | 2012-04-02 | 0 | 50 | 1 | 0 | 8 | -1 | 37 | 29 | -1 | -21 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 24 | 26 | 29
| Tuesday | 2012-04-03 | 0 | 50 | 3 | 0 | 12 | -3 | 41 | 29 | -3 | -21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 27 | 29 | 29
| Wednesday | 2012-04-04 | 0 | 50 | 2 | 1 | 9 | -1 | 35 | 26 | -1 | -24 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 3 | 0 | 21 | 24 | 26
| Thursday | 2012-04-05 | 0 | 50 | 0 | 3 | 9 | 3 | 33 | 24 | 3 | -26 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 20 | 23 | 24
| Monday | 2012-04-09 | 0 | 50 | 4 | 0 | 16 | -4 | 35 | 19 | -4 | -31 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 17 | 18 | 19
| Tuesday | 2012-04-10 | 0 | 50 | 3 | 3 | 15 | 0 | 35 | 20 | 0 | -30 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 18 | 19 | 20
| Wednesday | 2012-04-11 | 0 | 50 | 3 | 9 | 10 | 6 | 20 | 10 | 6 | -40 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 10
| Thursday | 2012-04-12 | 0 | 50 | 6 | 3 | 14 | -3 | 25 | 11 | -3 | -39 | 0 | 2 | 2 | 1 | 0 | 1 | 2 | 1 | 0 | 6 | 7 | 11
| Friday | 2012-04-13 | 0 | 50 | 5 | 6 | 15 | 1 | 19 | 4 | 1 | -46 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 4
| Monday | 2012-04-16 | 0 | 50 | 5 | 6 | 13 | 1 | 21 | 8 | 1 | -42 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 4 | 6 | 8
| Tuesday | 2012-04-17 | 0 | 50 | 5 | 0 | 26 | -5 | 37 | 11 | -5 | -39 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 8 | 9 | 11
| Wednesday | 2012-04-18 | 0 | 50 | 2 | 7 | 22 | 5 | 25 | 3 | 5 | -47 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 3
| Thursday | 2012-04-19 | 0 | 50 | 2 | 10 | 21 | 8 | 21 | 0 | 8 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Friday | 2012-04-20
Defect Definitions
| Blocker | Unavoidable or high frequency defect that is a non-progression or crash that stops the player from being able to continue the game. Including defects that force a refresh of the database.
| Critical | Avoidable or low frequency defect that can cause a non-progression or requires a refresh of the users browser.
| Major | Incorrect Gameplay based on design targets or functionality defects. Highly visual graphical defects or inconsistencies.
Note: QA are always defining bugs by Open Beta.

## Milestone Tracker
BZR EMPIRE INC.
PATTERN BATTLES - MILESTONE TRACKER
MILESTONE | DELIVERABLE | DUE DATE | STATUS | RELEASE | SVN LOCATION | NOTES
Ideation and preproduction | Definition of technologies | 2014-03-01 | SUBMITTED | LAUNCH
Ideation and preproduction | Definition of the multiplayer goals | 2014-03-01 | SUBMITTED | LAUNCH
Ideation and preproduction | Definition of the back-end architecture | 2014-03-01 | SUBMITTED | LAUNCH
Ideation and preproduction | Moodboard | 2014-03-01 | SUBMITTED | LAUNCH
Ideation and preproduction | User Flows based on initial game concepts. | 2014-03-01 | SUBMITTED | LAUNCH
Prototype | Core Engine | 2014-03-29 | ATTENTION | LAUNCH
Prototype | Server-Client communication | 2014-03-29 | ATTENTION | LAUNCH
Prototype | Definition of the user data | 2014-03-29 | SUBMITTED | LAUNCH
Prototype | First test on device | 2014-03-29 | SUBMITTED | LAUNCH
Prototype | Wireframes for key screens based on User Flows. | 2014-03-29 | SUBMITTED | LAUNCH
First Playable | Engine implemented | 2014-04-12 | ATTENTION | LAUNCH
First Playable | integrated solo player flow | 2014-04-12 | ATTENTION | LAUNCH
First Playable | All screens are represented | 2014-04-12 | ATTENTION | LAUNCH
First Playable | All transitions are represented | 2014-04-12 | ATTENTION | LAUNCH
First Playable | Definition of move representation | 2014-04-12 | SUBMITTED | LAUNCH
First Playable | Integration of the first UI | 2014-04-12 | SUBMITTED | LAUNCH
First Playable | Initial Game-play and UI Design Concepts. Initial Logo design concepts. | 2014-04-12 | SUBMITTED | LAUNCH
Pre-alpha | standard moves implemented | 2014-05-03 | ATTENTION | LAUNCH
Pre-alpha | UX complete | 2014-05-03 | ATTENTION | LAUNCH
Pre-alpha | definition of monetization | 2014-05-03 | ATTENTION | LAUNCH
Pre-alpha | definition of social interaction | 2014-05-03 | ATTENTION | LAUNCH
Pre-alpha | definition of app center interaction | 2014-05-03 | ATTENTION | LAUNCH
Pre-alpha | Deployed on device | 2014-05-03 | ATTENTION | LAUNCH
Pre-alpha | Refined UI concepts based on feedback from initial designs. | 2014-05-03 | ATTENTION | LAUNCH
Alpha | All moves implemented | 2014-05-24 |  | LAUNCH
Alpha | Enforced stability | 2014-05-24 |  | LAUNCH
Alpha | Finalized concepts for overall design direction of game. Most key screens represented. Logo refinement based on feedback. | 2014-05-24 |  | LAUNCH
Closed Beta | Finalized monetization | 2014-06-07 |  | LAUNCH
Closed Beta | Compatibility testing | 2014-06-07 |  | LAUNCH
Closed Beta | Iteration of UI design where needed for any outstanding screens. | 2014-06-07 |  | LAUNCH
Beta | Front-end debug | 2014-07-05 |  | LAUNCH
Beta | Back-end debug | 2014-07-05 |  | LAUNCH
Beta | Playtest feedback integration | 2014-07-05
Beta | Scalability testing | 2014-07-05
Beta | Refinement of UI based on feedback. Finalized Logo | 2014-07-05
Release | Debug | 2014-08-09
Release | Polishing | 2014-08-09
Release | integration with social interaction | 2014-08-09
Release | packaging to publish on mobile | 2014-08-09
Release | monetization packages | 2014-08-09
Release | Finalize all graphics based on any outstanding feedback. | 2014-08-09
Release | publishing game on app centers | 2014-08-09
Release | Deployment of back-end | 2014-08-09
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
Formulas:
DUE DATE = VLOOKUP([MILESTONE],data!$D2:E9,2, FALSE)

## data
status | date | STATUS 2 | milestone
SUBMITTED | 0 | On Track | Ideation and preproduction | 2014-03-01
ATTENTION | 1 | Off Track | Prototype | 2014-03-29
DEPRECATED |  | In Review | First Playable | 2014-04-12
BLOCKED |  | Needs Attention | Pre-alpha | 2014-04-26
TBD |  |  | Alpha | 2014-05-17
|  |  | Closed Beta | 2014-05-31
|  |  | Beta | 2014-07-05
|  |  | Release | 2014-08-09